PIXELCRAFT STUDIOS

Integrated Creative & Production Agency

RFQ RESPONSE — RFQ-MKT-KIDS-GL-2026-001

| Document Title | Commercial Proposal — Global Kids Health Drink Launch |
| --- | --- |
| RFQ Reference | RFQ-MKT-KIDS-GL-2026-001 |
| Submitted To | Global Brand Marketing Team |
| Prepared By | PixelCraft Studios Pvt. Ltd. |
| Contact | Ananya Mehrotra, VP – Client Solutions ¦ a.mehrotra@pixelcraft.in |
| Date | April 10, 2026 |
| Proposal Ref | PC-PROP-2026-KHD-01 |
| Version | FINAL — v3.0 |
| Validity | 60 days from submission date |

⚠  IMPORTANT: PixelCraft uses the term 'Project Fee' throughout this document to refer to total agency charges including all fees and applicable taxes, UNLESS otherwise specified. Media budgets and production pass-throughs are listed separately under 'Passthrough Costs'.

# TABLE OF CONTENTS

1. Executive Overview

2. PixelCraft Company Profile

3. Relevant Experience

4. Understanding of Brief & Scope

5. Our Strategic Approach

6. Creative Philosophy & Process

7. TVC Production Methodology

8. Digital & Social Content Framework

9. Compliance & Child Safety Protocols

10. Proposed Team

11. Project Timelines

12. Commercial Proposal

13. Payment Structure

14. Terms & Conditions

15. Appendices

# 1. Executive Overview

PixelCraft Studios is proud to present this comprehensive proposal for the global launch campaign of the new kids health drink. As one of India's leading integrated creative and production agencies with a dedicated kids and family vertical, we bring 16 years of proven expertise to this brief.

We have carefully reviewed the complete RFQ and the Scope of Work and are pleased to confirm that we can cover all 8 Line Items (Lots 1-8) in full, with no carve-outs or sub-contracting. Our in-house capabilities span strategy, creative, TVC production (with certified child talent protocols), digital content, paid media, compliance review, and program management.

## Why PixelCraft?

- 16 years of integrated marketing experience with particular depth in kids and family

- In-house TVC production studio in Mumbai — fully equipped for child talent shoots

- Dedicated compliance team with ASCI, FTC, and ASA-certified reviewers

- Team of 280 across 4 offices (Mumbai, Delhi, Bengaluru, London)

- 12 national awards in the kids and FMCG categories in the last 3 years

- Net Promoter Score of 87 from existing clients — among the highest in the industry

# 2. PixelCraft Company Profile

PixelCraft Studios was founded in 2008 by Ananya Mehrotra and Siddharth Chopra with a singular vision: to create communications that genuinely connect with real people. Starting as a boutique creative studio, we have grown into a full-service integrated agency with 280+ employees across four offices.

Our journey in the kids and family space began in 2012 when we won our first national kids brand account — a leading children's breakfast cereal. Since then, we have built one of India's most experienced kids marketing practices, with a dedicated team of 65 specialists.

PixelCraft is structured around four practice areas: Brand Strategy, Creative Production, Digital & Social, and Compliance & Governance. This structure ensures full-spectrum capability under a single agency relationship, eliminating coordination overhead for clients.

We maintain a London office (PixelCraft UK) specifically to manage European compliance requirements, UK/EU advertising regulations, and international production partnerships. This is particularly relevant for multi-market campaigns such as this one.

# 3. Relevant Experience

Over the past 16 years, PixelCraft has delivered 80+ integrated campaigns in the kids and family segment across FMCG, health, nutrition, and entertainment categories. Selected highlights are provided below.

Campaign: NutriKids Launch (Himalaya Drug Company, 2025). Full integrated campaign including strategy, TVC, social, and media. TVC featured 8 child actors across a 4-day shoot. Delivered 38% aided awareness within 6 months of launch. Won EFFIE Silver 2025.

Campaign: Complan Global Refresh (Kraft Heinz, 2024). Strategy refresh and TVC production for 6 markets including India, UAE, Bangladesh, Sri Lanka. Led compliance review across all markets. Campaign delivered 22% sales uplift in primary markets.

Campaign: KoolYog Kids Yogurt (Epigamia, 2023). First major kids campaign for this D2C brand. Social-first strategy with TVC anchor. Over 180 social assets created in year 1. Brand NPS improved from 32 to 61 within 12 months.

Full portfolio and case study decks available upon request. References from all three clients above are pre-approved and available for contact.

# 4. Understanding of Brief & Scope

We have thoroughly analysed the RFQ document and the Scope of Work for RFQ-MKT-KIDS-GL-2026-001. Our understanding of the brief is as follows.

The client seeks to launch a new kids health drink into a global market. The campaign must span multiple channels (TVC, social, digital) across multiple markets, and must navigate the complex regulatory environment of kids advertising across different geographies.

The 8 workstreams defined in the RFQ represent a comprehensive integrated marketing brief that requires both strategic and executional excellence. We note that the RFQ explicitly requires compliance with child safety and advertising standards, which aligns closely with our own non-negotiable principles.

Key challenges we anticipate: (1) Navigating different regulatory environments across markets with different rules for kids advertising; (2) Balancing aspirational brand messaging with accurate health claims; (3) Creating content that is genuinely appealing to kids while being trusted by parents; (4) Coordinating multi-workstream delivery while maintaining consistent brand voice.

# 5. Our Strategic Approach

Our strategic approach to this brief is built on the insight that kids health products face a dual audience challenge: they must appeal to children (who choose what they want) and parents (who decide what they buy). Most campaigns fail by trying to appeal to both simultaneously and resonating with neither.

We recommend a two-layer creative architecture: a primary kids layer featuring a playful, adventure-driven character and narrative, and a secondary parent layer providing functional reassurance on health benefits. Both layers are unified by a master brand platform but executed through platform-appropriate content.

Strategy Phase 1 (Weeks 1-4): Market immersion, category landscape mapping, consumer insight synthesis (existing research + 2 focus groups with parents), competitive audit, opportunity identification, and brand positioning statement.

Strategy Phase 2 (Weeks 5-8): Messaging architecture, creative territories development (3 directions), client review and territory selection, creative brief finalization, and TVC brief development.

This phased approach ensures the creative work is built on solid strategic foundations and reduces the risk of expensive production based on weak strategy.

# 6. Creative Philosophy & Process

At PixelCraft, we believe that the best kids advertising does not talk down to children. The most effective campaigns in this category treat kids as intelligent, curious, and capable of complex emotional responses. Our creative process starts from this principle.

We use a proprietary creative framework called SPARK (Story, Protagonist, Authenticity, Relevance, Kinetics) for all kids campaigns. This framework has been developed over 12 years and 60+ kids campaigns and consistently delivers work that tests strongly with both child and parent audiences.

Creative development at PixelCraft involves: strategic insight as the creative springboard; multi-format ideation across TV, digital, and experiential; co-creation sessions with kids (age-appropriate); rapid prototyping using animatics before full production; and rigorous compliance review before finalisation.

Our creative team for this project will be led by Rohan Krishnamurthy (Creative Director, 14 years) and Priya Nair (Senior Art Director, 10 years), both of whom have led award-winning kids campaigns in the past 3 years.

# 7. TVC Production Methodology

PixelCraft's in-house TVC production unit, PixelCraft Films, is fully equipped for commercial film production with specialisation in kids and family content. We maintain our own studio facility in Andheri East, Mumbai with dedicated child-safe production spaces.

Our production methodology for kids TVCs follows a 16-step process from brief intake to final delivery, including dedicated compliance checkpoints at pre-production, shoot, and post-production stages. This process has been audited and certified by an independent child welfare body.

Child Talent Management: We work exclusively with licensed talent agencies and maintain our own verified roster of 80+ child actors aged 5-14 across Mumbai, Delhi, and Bengaluru. All child actors on our roster are enrolled in our Talent Welfare Programme which includes mandatory health checks, welfare officer assignment, and parent education sessions before any shoot.

Post-Production: Our post-production facility handles all formats from broadcast master to social cutdowns in-house. We maintain final deliverables in a secure cloud repository with client access for 5 years post-delivery.

# 8. Digital & Social Content Framework

Our digital and social content approach for this campaign is built on a 'Content Engine' model — a structured, scalable content production system that ensures brand consistency across platforms while enabling platform-native execution.

The Content Engine for this campaign will produce: 12 anchor videos (1 per month, 60-90 seconds, cross-platform), 36 platform-specific short-form videos (12 per platform, 15-30 seconds), 120 static/carousel posts (10 per month), 60 Stories/Reels assets (5 per month per platform), and seasonal/topical content on an as-needed basis.

Platform Strategy: Meta (Facebook + Instagram) will focus on parent-facing content with functional messaging. YouTube will carry the long-form brand story content. TikTok will feature the most playful, kid-friendly content with participation hooks.

We propose a dedicated social content team of 6 for this account: 1 social strategist, 2 content creators, 1 graphic designer, 1 video editor, and 1 community manager. This team will be assigned exclusively to this account during the campaign period.

# 9. Compliance & Child Safety Protocols

PixelCraft maintains one of the most comprehensive child safety and advertising compliance frameworks in the Indian agency landscape. This framework has been independently audited and is reviewed annually by our legal team.

Our Compliance Framework covers: Pre-production (script review, claim verification, talent recruitment protocols); During production (on-set welfare officer, working hours compliance, safe environment protocols); Post-production (content review against platform policies, market-specific standards); and Media placement (age-appropriate environments, COPPA/GDPR compliance for digital).

Market Coverage: We have direct compliance expertise in India (ASCI, FSSAI, BIS), UK (ASA, CAP), UAE (NMC), and Singapore (ASAS). For USA, Australia, and other markets, we work with our established compliance partner network.

Claims Review: All health and nutritional claims go through a 4-step review process: (1) Internal legal review; (2) Client R&D substantiation; (3) Market-specific regulatory review; (4) Final sign-off by Senior Compliance Director. No claims are published without this complete process.

# 10. Proposed Team

The following core team will be dedicated to this account. All team members are confirmed available.

Ananya Mehrotra — Account Director (VP, 18 years experience). Overall account ownership, senior client relationship, quality oversight.

Rohan Krishnamurthy — Creative Director (14 years). Creative leadership, TVC concept development, campaign vision.

Priya Nair — Senior Art Director (10 years). Key visual development, campaign visual identity, digital creative.

Vikram Joshi — Production Director (16 years). TVC production management, casting, post-production oversight.

Farah Khan — Social Media Director (9 years). Content strategy, community management, influencer partnerships.

Amit Gupta — Paid Media Director (11 years). Media strategy, planning, buying and optimization.

Dr. Leela Sharma — Compliance Director (8 years). Compliance framework, script review, market-specific sign-offs.

Karan Mehta — Project Director (7 years). Day-to-day project management, timelines, stakeholder coordination.

# 11. Project Timelines

The following indicative timeline has been developed based on the RFQ's specified deadlines. All timelines assume client-side approvals within 3 working days unless otherwise agreed.

Week 1-2: Project kick-off, team onboarding, stakeholder interviews, brand immersion.

Week 3-5: Category research, consumer insight synthesis, competitive audit, brand positioning workshop.

Week 6-8: Creative territory development, client review, territory selection, TVC brief.

Week 9-11: TVC script development (2 options), storyboard, animatic, client review.

Week 12-15: Pre-production (casting, locations, crew, compliance pre-clearance).

Week 16-18: TVC shoot (3-4 days), on-set compliance sign-off, footage review.

Week 19-23: Post-production, VFX, colour, sound, cutdowns, QC.

Week 24: TVC master delivery, format delivery, compliance certificates.

Week 14 onwards: Social content engine running in parallel — Month 1 calendar live.

Week 20 onwards: Paid media campaigns live, with weekly optimization reports.

Week 26-52: Ongoing social content delivery, media optimization, quarterly reviews.

# 12. Commercial Proposal

⚠  TERMINOLOGY NOTE: In this document, 'Project Fee' = total agency charges inclusive of GST (18%). 'Agency Fee' = fee exclusive of GST. 'Total Cost' = synonym for Project Fee in summary tables. 'Passthrough Costs' = media spends, OOP expenses — billed separately at actuals. Evaluators should use 'Total Agency Fee (excl. GST)' for like-for-like comparison.

## 12.1 Lot-wise Summary — Total Cost Overview

| Lot # | Workstream | Agency Fee (ex-GST) | GST (18%) | Project Fee (incl. GST) |
| --- | --- | --- | --- | --- |
| 1 | Strategy & Creative Development | ₹32,00,000 | ₹5,76,000 | ₹37,76,000 |
| 2 | TVC Development | ₹24,50,000 | ₹4,41,000 | ₹28,91,000 |
| 3 | TVC Production | ₹54,00,000 | ₹9,72,000 | ₹63,72,000 |
| 4 | Social Organic Content (12 months) | ₹38,00,000 | ₹6,84,000 | ₹44,84,000 |
| 5 | Paid Media Planning | ₹12,50,000 | ₹2,25,000 | ₹14,75,000 |
| 6 | Paid Media Buying & Optimization | ₹28,00,000 | ₹5,04,000 | ₹33,04,000 |
| 7 | Kids Advertising Compliance Review | ₹18,00,000 | ₹3,24,000 | ₹21,24,000 |
| 8 | Launch Program Management | ₹22,00,000 | ₹3,96,000 | ₹25,96,000 |
|  | Total Agency Fee (ex-GST) | ₹2,29,00,000 | ₹41,22,000 |  |
|  | Total Cost / Project Fee (incl. GST) |  |  | ₹2,70,22,000 |

⚠  The above 'Total Cost' / 'Project Fee' covers agency fees only. Recommended media spend (passthrough) for global launch period: INR 8-12 Crore (client-funded). PixelCraft charges no commission on media — billed at net rates with full transparency.

## 12.2 Lot 1 & 2 — Detailed Breakdown: Strategy & Creative

| # | Deliverable | Qty | Unit Rate (₹) | Total (₹) |
| --- | --- | --- | --- | --- |
| 1.1 | Brand Strategy Workshop & Report | 1 | 5,00,000 | 5,00,000 |
| 1.2 | Consumer Insight Synthesis | 1 | 2,50,000 | 2,50,000 |
| 1.3 | Messaging Architecture | 1 | 3,00,000 | 3,00,000 |
| 1.4 | Creative Territory x3 | 3 | 4,50,000 | 13,50,000 |
| 1.5 | Key Visual Development | 1 | 3,50,000 | 3,50,000 |
| 1.6 | Master Campaign Toolkit | 1 | 4,50,000 | 4,50,000 |
|  | LOT 1 SUBTOTAL |  |  | ₹32,00,000 |
| 2.1 | TVC Script (x2 options) | 2 | 3,00,000 | 6,00,000 |
| 2.2 | Full Storyboard | 1 | 2,50,000 | 2,50,000 |
| 2.3 | Animatic | 1 | 4,50,000 | 4,50,000 |
| 2.4 | Packshot Plan & Product Script | 1 | 1,50,000 | 1,50,000 |
| 2.5 | Creative Supervision — Production | 1 | 5,50,000 | 5,50,000 |
| 2.6 | Post-Production QC & Supervision | 1 | 4,50,000 | 4,50,000 |
|  | LOT 2 SUBTOTAL |  |  | ₹24,50,000 |

## 12.3 Lot 3 — TVC Production Breakdown

| # | Production Line Item | Qty | Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- |
| A | PRE-PRODUCTION |  |  |  |
| A1 | Director Fee (Award winner — kids specialist) | 1 | 4,00,000 | 4,00,000 |
| A2 | DOP + Camera Team | 1 | 2,20,000 | 2,20,000 |
| A3 | Child Talent (Lead x2, Supporting x4) | 6 | Varied | 9,80,000 |
| A4 | Adult Talent (x2) | 2 | 85,000 | 1,70,000 |
| A5 | Child Welfare Officer (on-set, all days) | 1 | 90,000 | 90,000 |
| A6 | Production Design + Wardrobe | 1 | 2,80,000 | 2,80,000 |
| A7 | Pre-production Admin & Logistics | 1 | 1,50,000 | 1,50,000 |
|  | Pre-Production Subtotal |  |  | 22,90,000 |
| B | SHOOT EXECUTION (4 Days) |  |  |  |
| B1 | Studio Hire — PixelCraft Films, Mumbai (4 days) | 4 | 2,00,000 | 8,00,000 |
| B2 | Equipment Package (Camera + Lighting) | 4 | 1,20,000 | 4,80,000 |
| B3 | Crew (18-person) | 4 | 3,20,000 | 12,80,000 |
| B4 | Catering (50 pax) | 4 | 52,000 | 2,08,000 |
| B5 | Production Consumables + Misc | 1 | 1,20,000 | 1,20,000 |
|  | Shoot Subtotal |  |  | 28,88,000 |
| C | POST-PRODUCTION |  |  |  |
| C1 | Offline Editing (60s + 30s masters) | 2 | 2,20,000 | 4,40,000 |
| C2 | VFX & Motion Graphics (product CG) | 1 | 3,80,000 | 3,80,000 |
| C3 | Colour Grading (DaVinci) | 1 | 1,80,000 | 1,80,000 |
| C4 | Sound Design + Music Composition | 1 | 3,20,000 | 3,20,000 |
| C5 | Format Cutdowns (8 digital formats) | 8 | 50,000 | 4,00,000 |
| C6 | Final Delivery + Cloud Archive | 1 | 1,02,000 | 1,02,000 |
|  | Post-Production Subtotal |  |  | 18,22,000 |
|  | LOT 3 TOTAL AGENCY FEE (ex-GST) |  |  | ₹54,00,000 |

## 12.4 Lots 4-8 — Summary (Detailed sheets on request)

| Lot | Workstream | Key Deliverables | Agency Fee (ex-GST) |
| --- | --- | --- | --- |
| 4 | Social Organic Content | 288 assets/yr, 3 platforms, content calendar, community mgmt | ₹38,00,000 |
| 5 | Paid Media Planning | Annual plan + quarterly plans, audience strategy | ₹12,50,000 |
| 6 | Paid Media Buying & Opt. | Campaign setup, 12-month management, weekly reports | ₹28,00,000 |
| 7 | Compliance Review | All markets, all formats, compliance certificates x8 | ₹18,00,000 |
| 8 | Program Management | Full-time PM lead + coordinator, 12 months | ₹22,00,000 |

# 13. Payment Structure

PixelCraft proposes milestone-based payments aligned to key delivery points. All amounts below are exclusive of GST (18% applicable on each invoice).

| Milestone | Payment % | Amount (₹, ex-GST) | Trigger |
| --- | --- | --- | --- |
| Project Mobilisation | 20% | ₹45,80,000 | Within 10 days of LOI |
| Strategy & Creative Lock | 15% | ₹34,35,000 | On territory approval |
| TVC Pre-Production Complete | 15% | ₹34,35,000 | 1 week before shoot |
| TVC Master Delivery | 20% | ₹45,80,000 | On final delivery |
| Month 6 Review | 15% | ₹34,35,000 | Month 6 |
| Campaign Close & Final Report | 15% | ₹34,35,000 | On final report delivery |
| TOTAL | 100% | ₹2,29,00,000 |  |

# 14. Terms & Conditions

### 14.1 Validity

This proposal is valid for 60 days from April 10, 2026.

### 14.2 Currency

All fees are in Indian Rupees (INR). GST at 18% is applicable on all fees.

### 14.3 Exclusions

Media budgets/spends are excluded and billed as passthrough at net rates. Travel and out-of-pocket expenses for outstation requirements are billed at actuals.

### 14.4 IP Ownership

All creative IP vests with the client upon full payment.

### 14.5 Scope Changes

Changes to scope require a formal Change Order document before implementation.

### 14.6 Confidentiality

This document is strictly confidential.

### 14.7 Governing Law

Laws of India. Jurisdiction: Mumbai courts.

# 15. Appendices

## Appendix A: PixelCraft Studios — Registration Details

| Company Name | PixelCraft Studios Private Limited |
| --- | --- |
| Registered Office | Unit 501, Infinity Tower, Andheri East, Mumbai 400069 |
| CIN | U74999MH2008PTC123456 |
| GST Number | 27AABCP9876M1Z3 |
| PAN | AABCP9876M |
| MSME Status | Medium Enterprise (udyam reg no: MH-01-0000123) |
| Bank | HDFC Bank, Andheri Branch ¦ A/c: 50XXXXXXXX ¦ IFSC: HDFC0003456 |

## Appendix B: Compliance Certifications (attached separately)

The following certifications are provided as separate attachments: (1) ASCI Membership Certificate; (2) ISO 9001:2015 Quality Management Certificate; (3) Child Welfare Officer Certification — Dr. Leela Sharma; (4) PixelCraft UK — ASA Member Certificate; (5) Sample Compliance Checklist Template.

## Appendix C: Selected Agency Showreel

Access our kids and family category showreel at: https://vimeo.com/pixelcraft/kidsfamily2025 (Password: PC2026)

Thank you for considering PixelCraft Studios for this exciting assignment. We are fully committed to delivering world-class work and look forward to the opportunity to partner with the Global Brand Marketing Team.

Ananya Mehrotra | VP – Client Solutions

a.mehrotra@pixelcraft.in | +91-9876123456

PixelCraft Studios Pvt. Ltd. | pixelcraft.in